## Overview
Welcome to Our UAT!
UAT Overview
|  | TEST DATE: | 2023-04-24 |  | TEST ENVIRONMENT | Sandbox, Test
|  | TEST COVERAGE: | Adding line slip data |  | TEST PARTICIPANTS: | Sylvan, Lorrie, Stephen, Bryan, Angela
Manage written lines
Manage signed lines
|  |  | Download documents in excel |  | TEST COORDINATOR: | Karaleise
Capture risk details
Create insurance reports
Manage programs
Manage layers
Manage UW authority limits
| Test Completion |  |  |  | Bugs by Priority
Bugs by Feature
Bugs by status

## UAT Bug Tracking
ORCA BUG TRACKING LIST
To be completed by project team
TEST AREA | DESCRIPTION | SCREEN CAPTURE | CLIENT | REPORTED BY | STATUS | BUG TYPE | DevOps TICKET # | PRIORITY | COMMENTS
Line Slip Data | Unable to save Slip data. Getting 504 error when I click save |  | Hilton Hotel | Karaleise | Open | Missed requirement |  | Critical |  |  | Status Chart Data
Manage signed lines |  |  |  |  | Fixed |  |  | High |  |  | Open | 5
Line Slip Data |  |  |  |  | In progress |  |  | High |  |  | Fixed | 3
Risk assessment |  |  |  |  | Open |  |  | Critical |  |  | In progress | 4
Line Slip Data |  |  |  |  | Open |  |  | Medium |  |  | Won't Fix | 2
Line Slip Data |  |  |  |  | Open |  |  | Medium |  |  | Deferred | 2
Risk assessment |  |  |  |  | Won't Fix |  |  | Medium
Manage signed lines |  |  |  |  | Fixed |  |  | High
Manage written lines |  |  |  |  | In progress |  |  | Low
Line Slip Data |  |  |  |  | In progress |  |  | Low
Manage signed lines |  |  |  |  | In progress |  |  | High |  | Priority Chart Data
Manage signed lines |  |  |  |  | Open |  |  | High |  |  | Critical | 2
Manage signed lines |  |  |  |  | Fixed |  |  | Low |  |  | High | 6
Manage written lines |  |  |  |  | Won't Fix |  |  | Low |  |  | Medium | 3
Manage written lines |  |  |  |  | Deferred |  |  | High |  |  | Low | 4
Manage written lines |  |  |  |  | Deferred
Document management
Risk assessment
Reports | [9 empty] | Progress Chart Data
Document management | [10 empty] | Tests Completed | 6
Document management | [10 empty] | Not Yet Completed | 3
Document management
Document management
Manage programs | [9 empty] | Feature Chart
Manage layers | [10 empty] | Adding line slip data | 7
Risk assessment | [10 empty] | Manage written lines | 4
Line Slip Data | [10 empty] | Manage signed lines | 5
Line Slip Data | [10 empty] | Document management | 5
Underwriting Authority | [10 empty] | Risk assessment | 4
[11 empty] | Reports | 1
[11 empty] | Manage programs | 1
[11 empty] | Manage layers | 1
[11 empty] | Underwriting Authority | 1

## Empty State Test
TEST 1 - EMPTY STATE
SETUP
ENVIRONMENT: Sandbox
USERNAME:
PASSWORD:
PRECONDITION
Account must be new with no prior applications
TEST OBJECTIVE
Confirm that the system will detect empty states and prompt the user with onboarding options.
|  |  | WORKFLOW STEPS | EXPECTED RESULTS | COMMENTS
|  | 1 | Login as regular user
|  | 2 | Create an application | System detects that no application exists and prompts to create an application.
|  | 3 | Click next on all the steps for the application creation wizard, but do not save the application.
|  | 4 | Verify that you are not able to click manage application | Manage application is grayed out since there are no apps
|  | 5 | Verify that you are not able to export application
|  | 6 | Verify that you are not able to copy an application
|  | 7 | Verify that you are not able to merge an application
|  | 8 | Verify that the application report option is not active
| Tester | Test Completed?
| Bryan | Yes
| Angela | Yes
| Stephen | Yes
| Sylvan | Yes
| Lorrie | No

## Add line Slip
TEST 1 - Line Slip Data Entry
SETUP
ENVIRONMENT: Sandbox
USERNAME:
PASSWORD:
PRECONDITION
Line slip data:link
TEST OBJECTIVE
Confirm that the system will allow entering line slip data and validate data fields based on our business rules.
|  |  | WORKFLOW STEPS | EXPECTED RESULTS | COMMENTS
|  | 1 | Access orca system | Able to see landing page
|  | 2 | Search for client
|  | 3 | Enter the line slip details | System will accept line slip data and validate where required fields. | Confirm that the line slip number is 7 characters
|  | 4 | Remove premium amount | System will display an error that says premium is required.
|  | 5 | Verify that you are not able to export line | No export option is shown
|  | 6 | Verify you are able to upload documents for the line slip | Upload documents option is shown with file size limit of 300MB
|  | 7 | Verify that you are not able to merge an application
|  | 8 | Verify that the application report option is not active
| Tester | Completed?
| Bryan | Yes
Angela
| Stephen | Yes
| Sylvan | Yes
Lorrie

## New Application Test
TEST 2 - Manage signed and written lines
SETUP
ENVIRONMENT: Preview
USERNAME:
PASSWORD:
SSN: 777-51-7777
PRECONDITION
Account must be active
TEST OBJECTIVE
Confirm that the system can handle the creation of new applications and does application evaluation accurrately
|  |  | WORKFLOW STEPS | EXPECTED RESULTS | COMMENTS
|  | 1 | Open line slip data in Orca
|  | 2 | Change the value for the written line | System detects that there was a change and prompts to confirms
|  | 3 | Confirm that confirmation was sent to your phone
|  | 4 | Change verification to email and confirm | Manage application is grayed out since there are no apps
|  | 5 | Enter the test ssn and confirm that the credit scores are pulled
|  | 6 | verify that when ssn isentered the application prepopulates the credit data fields
|  | 7 | Submit application and verify you receive confirmation email
|  | 8 | Repeat 1-7 on mobile phone
| Tester | Completed?
Bryan
| Angela | Yes
| Stephen | Yes
| Sylvan | Yes
Lorrie

## UAT Prep Tasks
UAT Tasks
DevOps to update the testing environment with real world data - create clients
Prepare the line slips for testers
Discuss UAT approach with project team
Determine dedicated QA to write UAT bugs in DevOps
Determine UAT team to set bug fix priority ( product owner/project manager, BA and QA)

## _56F9DC9755BA473782653E2940F9 (hidden)
8NxXgzDa6kapAjOE4RZQ1NQqE6ahwlxOuUPxngRik9lUNlVONFUxUE1QRkJGRkw1SFkzM0gwQTQzVS4u
Form1
{b1488e88-c700-48b1-9878-d32ee2984818}